## Orig plan-BPP
DRAFT PROJECT PLAN FOR COACHING POSTDOCS TO COMPLETE a K-APPLICATION
Topic / Activity | in-Person or Virtual | Preparation | Outcomes/Next steps | Follow up req'd? | Links to references | prep time | on-site meeting w/ travel | off-site group facilitation | follow-up
PREPARATION PHASE | [5 empty] | 5-6 weeks
Meeting | P |  |  |  |  | 2 | 1 |  | 0.5
Review the process we will go through |  | read parent K01 FOA | re-read any parts that are still not clear
Review the FOA and SF424, highlighting impt areas |  | read SF424 |  |  | (esp 7.5)
Introduce Project Hub
Meeting | P |  |  |  |  | 2 | 1 |  | 0.5
Discuss selection of institute/center |  | read I/C specific requirements
Ready any associated NOT or PAR |  | read due dates web page
Discuss selection of mentoring team |  | read requirements for mentoring team | select/contact/consider members of mentoring team | y
Discuss Letters of reference (3-5) |  | read requirements for Letters of Reference | begin to make list of possible referees | y | 7.3.
Review Project Hub, get project spaces
Meeting | V |  |  |  |  | 1 |  | 1 | 0.5
Discuss biosketches |  | read biosketch requirements and draft biosketch | revise biosketch |  | 7.4.4 & more
upload biosketch draft to Project Hub
Review and discuss review criteria |  | read review criteria
Discuss review criteria scoring matrix
Meeting | V |  |  |  |  | 1 |  | 1 | 0.5
Review how to generate attachments; fonts etc |  | re-read SF424 section on attachments |  |  | 7.5.2
Review page limit rules |  | read SF424 and nih web page on page limits |  |  | 7.5.2
Review list of sections that need to be written and order in which we will write them |  | re-read SF424 section on parts of the application | upload any docs/notes to the Hub |  | 7.5.2
Meeting | V |  |  |  |  | 1 |  | 1 | 0.5
Get clear on what your mentor and/or members of the mentoring team have to do |  | make sure mentors are confirmed | Make sure your mentors know what they have to do
8. Description of Institutional Environment |  | ask your mentor who is going to write this | ask them | y
9. Institutional Commitment to Candidate’s Research Career Development |  | ask your mentor who is going to write this | ask them | y
Make sure you know who your references will be |  |  | Contact references; give them form letter and tell how to submit
Meeting | P |  |  |  |  | 2 | 1 |  | 0.5
Budgets -- salary, fringe benefits, research development support, indirects (F&A) |  | read SF424 sections; and FOA
The electronic application process -- what the institution does behind the scenes, what the investigator needs to do and needs to be aware of, registering with eRA Commons and getting an eRA Commons ID |  | read SF424 sections and NIH website
[6 empty] | 9 | 3 | 3 | 3
WRITING SPECIFIC SECTIONS (of the PHS 398 Career Development Award Supplemental Form) | [5 empty] | 12 meetings over 3 months; 5 in person, 7 virtual
For each section below the process will be: review instructions; write detailed outline; fill in outline; write 1st draft; solicit feedback; revise; repeat as necessary
Meeting | P
Stress importance of following instructions; make sure everyone knows all the instructions they are supposed to be following. Set a structure for numbering and tracking documents. |  | Make 9 docs of instructions, one for each section numbered 2-5;7-11 (sections 1 and 6 are not applicable). Each doc will include ALL the instructions regarding "Candidate Background" , from the parent FOA, any I/C specific FOA and the SF424 | Revise instructions, as appropriate.
Receive training on outlining, and on other approaches for writing a first draft. |  |  | Draft a detailed outline for 2. Candidate Background
Meeting | V
2. Candidate's Background
Meeting | TBD
3. Career Goals and Objectives
This will probably require more than 1 week.
Meeting | TBD
10. Specific Aims
This will require more than 1 week.
Receive training on writing Specific Aims
Meeting | TBD
11. Research Strategy
This will require more than 1 week.
During this time we will make sure that items 7, 8 and 9 are in progress.
Meeting | V
7. Statements by Mentor, Co-mentor(s), Consultants, Contributors |  | make sure this is in progress
8. Description of Institutional Environment |  | make sure this is in progress or that you have it
9. Institutional Commitment to Candidate’s Research Career Development |  | make sure this is in progress or that you have it
Reference letters |  | make sure all references have uploaded their letters
Meeting | TBD
4. Career Development/ Training Activities During Award Period
This will require more than 1 week.
Meeting | V
Facilities & Other Resources (Item 10, Other Project Info.) |  | obtain boilerplate from dept, BPP, PSOM, other
5. Training in the Responsible Conduct of Research |  | obtain boilerplate from BPP
Meeting | TBD
Project Summary/Abstract (Item 7, Other Project Info.)
Cover letter |  |  |  |  | 7.4.7 (5.2)
NOTES
the numbered, and yellow highlighted cells represent separate sections of the "PHS 398 Career Development Award Supplemental Form" that must be completed and uploaded as separate documents
the colored cells in column F represent tasks that need follow up
so that postdocs in the cohort can collaborate, we will use Project Hub, a free project management application from Pbworks; each postdoc will have their own project within the K01 project space
[5 empty] | subtot phase II | 12 | 5 | 7 | 6
Beginning July 16, 2013: Items I forgot, above
title - 81 characters | [5 empty] | prep time | on-site meeting w/ travel | off-site group facilitation | follow-up |  | total meetings
figure out how to include all of these: http://www.niaid.nih.gov/researchfunding/grant/strategy/Pages/3researchstrategy.aspx |  |  |  |  | TOTALS | 21 | 8 | 10 | 9
example applications: http://www.niaid.nih.gov/researchfunding/grant/pages/appsamples.aspx |  |  |  |  | revised | 27 | 8 | 10 | 9
4
[6 empty] | 1620 | 2080 | 900 | 540 | 5140
[6 empty] | prep | on campus | remote | followup
[5 empty] | hours | 27 | 12 | 10 | 18
[5 empty] | rate | 60 | 250 | 175 | 60
[6 empty] | 1620 | 3000 | 1750 | 1080 | 7450
[6 empty] | prep | on campus | remote | followup
[5 empty] | hours | 27 | 13.5 | 9 | 18 | 67.5
[5 empty] | rate | 75 | 150 | 125 | 75
|  |  | give discount |  |  | 2025 | 2025 | 1125 | 1350 | 6525
Note on F2: Rachel: to be completed as we progress

## All items needed K
Number on the form | Item | Who writes | Page / length limit | Instructions / notes
11 | Descriptive Title of Applicant's Project | me |  | 200 characters
21 | Cover Letter Attachment | me | 1 ? | "applicants must include a cover letter that contains a list of referees (including name, departmental affiliation, and institution)"
| Letters of reference (3 to 5 of them) | me draft/ referees revise |  | NIH provides instructions; check eRA commons to make sure referees upload letters by due date; you will receive an email when referee submits
7 | Project Summary/Abstract | me | 30 lines
8 | Project Narrative | me | 3 sentences
9 | Bibliography and References Cited | me | no limit
10 | Facilities & Other Resources | get boilerplate | no limit
11 | Equipment | get boilerplate | ?
12 | Other Attachments | me |  | probably will not use this
| Biosketch -- me | me | 5
| Biosketches -- Mentor, Co-mentor, Other Senior/Key Persons (which probably means all members of Advisory Committee, plus anyone else who will contribute significantly scientifically) | get | 5 pages per person | need from people who contrib in substantial meaningful way to scientific development or execution
L | Budget and Budget Justification | me and BA
2 | Candidate Information and Goals for Career Development (3 sections: Background, Goals, Activities) | me | in the 12 | will probably be 4 or 5 pages total
3 | Specific Aims |  | 1
4 | Research Strategy (Significance, Innovation, Approach) |  | in the 12 | will probably be 8 or 7 pages total
6 | Training in the Responsible Conduct of Research | get boilerplate | 1
7 | N/A for K01, K08, K23
8 | Plans and Statements of Mentor and Co-mentor(s) | mentors | 6 | append all into 1 pdf
9 | Letters of Support from Collaborators, Contributors, and Consultants | I am pretty sure this is where letters from your Advisory Cmte members go | 6 | append all into 1 pdf
10 | Description of Institutional Environment | me, boilerplate | 1 | includes physical and collegial environment
11 | Institutional Commitment to Candidate’s Research Career Development | dept chair or similar | 1 | we will protect her time to 75% and not contingent upon receipt of this award
12 | Vertebrate Animals | me
13 | Select Agent Research | me
14 | Consortium/Contractual Arrangements | me
15 | Resource Sharing | me
16 | Authentication of Key Biological and/or Chemical Resources | me | 1
17 | Appendix | me |  | probably will not use this; check SF424 and FOA for allowable items
multiple fields | Human Subjects and Clinical Trials Information | me | no limits on length | This info is in section 500 of SF424 App'n Guide
| Scientific areas of expertise needed to review your application (optional) | me | 40 characters / field | up to 5 fields (which correspond to sci. areas)
SF 424 (R&R) Form
Letters of Reference-you request, referees upload into eRA commons
R&R Other Project Information Form
R&R Senior/Key Person Profile (Expanded) Form
R&R Budget Form
PHS 398 Career Development Supplemental Form
PHS Human Subjects and Clinical Trials Information
PHS Assignment Request Form